## August_daily_activites
DATE | Name | Action Item's for the day | Status of the work | Planned Work For Tomorrow | Remarks
2026-08-03
| Bhavya | 1. Implement search for all the files of IntegrateUs sharepoint 2. Working with Jama to evaluate best model to generate data profile. | 1. Discussion with jama regarding profile data generation for 1.2 hrs | 1. Implement search for all the files of IntegrateUs sharepoint.
| indra | 1. Complete all action items of 1st & 2nd august in the Search project. 2. Prepare an agent orchestrator for the Search. 3. Prepare SQL schema diagram for Search platforms. 4. | 1. Completed the actions items of 1st & 2nd august of search project 2. Drafted the architecture diagram of Search sytem orchestrator. 3. Prepared the SQL file for Schema creation and intial setup.
| sai b | I am working on the linkedin chrome extension. | Still in rnd | I need to work on the linkedin extension
| G jama | 1. go through proposed architecture 2.create detailed report of problem statement 3.create a action for implement that boon's county project | 1.Understand arcitecture 2.created report 3.created action for project | 1.working on datasets
| Harshith | I am working on the implementaion plan of boone county
2026-08-04
| Bhavya | 1. Implement search for all the files of IntegrateUs sharepoint. | Permissions are fetched into data tables, but there a lot changes needs to be done because of permissions levels and sync. | 1. Implement search for all the files of IntegrateUs sharepoint.
| indra | 1. Complete the action items of 3rd and 4th august of search project. 2. Review the SQL file and table creation. 3. Test CSP & UCAP E2E . 4. Prepare best quality questions from DIR Search for madhu. 5. R&D on Agent orchestrator and find out whether this approach helpful or not. | 1. Completed the action items in Search project. 2. SQL file script reviewed and fixed changes. 3. Questions are prepared and discussed with Rajeev 4. Need to review the agent orchestrator and discussed with Rajeev. 5. Fixed issues on deployment dir & PMCS Search by Rajeev. 6. Fixed issues in MVP1
| sai b | Working on the linkedin cherome extension | I have done some reasearch on the extension automation,so we cannot automate the installation of the extension | I need to work on the bids, resume chatbot, n8n automation for the transcript generation
| G jama | 1.working on datasets | i did't find any datasets for use case but found some related | 1. building workflowof bcjc
Harshith
2026-08-05
| Bhavya | 1. List out all the pain points of sync of live sharepoint data 2. Should find a way to process PPTs, Excels, etc files. | 1. A 50 mins dicussion with Jama & Harshit regarding Automated Non-Emergency calls for Boone County and delivered a base level demo. | 1. List out all the pain points of sync of live sharepoint data 2. Should find a way to process PPTs, Excels, etc files. 3. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation. 4. Collaborate with Jama and Harshith to deliver a demo for Automated Non-Emergency calls proposal.
| indra | 1. Run code review on search project. 2. E2E Testing on Search Product (Customer search platorm + UCAP ) 3. Write Unit and integrate test cases to validate UCAP & CSP & sync 4. Merge search project ui into customer portal ui | 1. Code review completed on UCAP & CSP 2. Manual review of UCAP going on. 3. Generated Testcases for UCAP & CSP & to validate sync. 4. Merged Search project UI into customer portal ui to remove inconsistency and redundancy 5. Manual UCAP UI testing and Identifying bugs and fixing them.
| sai b | I worked on the bids and the resume chat bot | Bids are done, resume chat bot is pending | I need to work one th n8n Automationa and the resume chatbot
| G jama | 1. building workflowof bcjc | Presented workflow | Implementation of BCJC Core logic
Harshith
2026-08-06
| Bhavya | 1. List out all the pain points of sync of live sharepoint data 2. Should find a way to process PPTs, Excels, etc files. 3. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation. 4. Collaborate with Jama and Harshith to deliver a demo for Automated Non-Emergency calls proposal. | In progress | 1. List out all the pain points of sync of live sharepoint data 2. Should find a way to process PPTs, Excels, etc files. 3. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation. 4. Collaborate with Jama and Harshith to deliver a demo for Automated Non-Emergency calls proposal.
| indra | 1. Complete all pending workflows from UCAP ,CSP. 2. Merge search project api into customer search portal api. 3. Review the orchestrate logic and get requirements to test it in Azure GPU VM. 4. Dry Run optimised pipeline in Mac | 1. Completed Testing on UCAP on customer creation and product assignment. 2. Completed Testing on Onboarding Validate invite 3. Merged search project api into customer portal api.
| sai b | I am working on the indian jobboard and resumechatbot and n8n automation | still pending | i need to add some locations and the addidtional feilds in the indian jobboard and i need to verify how the resume chatbot is working
| G jama | Implementation of BCJC Core logic | Implemented BCJC Core logic | evaluting with examples or synthtetic data of call tanscripts
Harshith
2026-08-07
| Bhavya | 1. List out all the pain points of sync of live sharepoint data 2. Should find a way to process PPTs, Excels, etc files. 3. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation. 4. Collaborate with Jama and Harshith to deliver a demo for Automated Non-Emergency calls proposal. | In Progress | 1. Work on the search logic and automation of the catalog and autocomplete 2. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation.
| indra | 1. Organise the DIR Demo solution. 2. Merge contracts search into DIR Demo solution. 3. Get credentials for Azure &GCP to test onboarding. 4. If Creds available, do the onboarding test trails. 5. Test UCAP & CSP Sync locally. | 1. Fixed Ui Cors error issues. 2. Added deployment activity tracker 3. disbaled email actvity tracking (testing purpose) 4. Search wizard is in sync with products marketplace. 5. Redesigned Customer portal login page and added product marketplace.
| sai b | I am working on the indian jobboard and the resume chatbot | 1. indian jobboard is done.I have dded the some locations and sections in the jobboard 2.Resume chat is also done | I need to work on the n8n automation for the transcript generation of monthly and weekly , daily
| G jama | evaluting with examples or synthtetic data of call tanscripts | evalutaed with synthtetic data of call tanscripts | implement STT/TTS and dashboard and improve logic performance
Harshith
2026-08-10
| indra | 1. Azure credentials created for Unnanu cloud. 2. Onboarding and Platform Sync enabled. 3. merged onboarding tab into deployment tab in platform. | 1. Azure credentials created for Unnanu cloud. 2. Onboarding and Platform Sync enabled. 3. merged onboarding tab into deployment tab in platform.
| Bhavya | 1. Work on the search logic and automation of the catalog and autocomplete 2. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation. | Working with Jama regarding Non-Emergency Call Demo and implemented classification techniques. | 1. Work on the search logic and automation of the catalog and autocomplete 2. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation.
| G Jama | implement STT/TTS and dashboard and improve logic performance | implemented that STT/TTS systems and find drawbacks | solve that drawbacks in core logic and created a doc of everything end to end project
2026-08-11
| Bhavya | 1. Work on the search logic and automation of the catalog and autocomplete 2. R&D on open & closed-source audio/video models (Whisper, Deepgram, Gemini 1.5 Pro) and collaborate with Tapasya to finalize the ML pipeline model catalog for metadata generation. | 1. Presented Current search logic and process with NNR sir and got some inputs from him and should R&D on the sharepoint Live search Technique. | 1. Complete R&D on new search logic and live sharepoint search process and tools. 2. Later submit Architecture, requirements, WorkFlow, PainPoints, and Walkthrough.
| indra | 1. Go through search APi manual review. 2. Dry run unnanu cloud test installing csp. 3. Sit with bhavya & Tapasya Regarding document optimisation. | 1. Merged all platforms and updated the git repo's 2. Created branches Main,uat,dev,indra applying all those approaches to entire search products
| G Jama | solve that drawbacks in core logic and created a doc of everything end to end project implemented spanish lang and emergency escalate report | finished core logic based on nyc data finished that spanish lang and emergency calls | implemented spanish lang and emergency escalate report if any call occurs what kind of meta data they required to ask caller
2026-08-12
| Indra | 1. AI search controller manual review | 1. Autocomplete question part is completed manually
| Bhavya | 1. Complete R&D on new search logic and live sharepoint search process and tools. 2. Later submit Architecture, requirements, WorkFlow, PainPoints, and Walkthrough. | Working on the logic and trying to implement for a demo | 1. Complete R&D on new search logic and live sharepoint search process and tools. 2. Later submit Architecture, requirements, WorkFlow, PainPoints, and Walkthrough.
| G Jama | if any call occurs what kind of meta data they required to ask caller | 1.retrived a 911 transcripts from different sources 2.discussing building logic with rajeev sir and nnr sir 3.drawbacks and improvments suggested rajeev sir | 1.Improvements on core logic 2.analysis on transcripts of 911 calls metadata
2026-08-13
| indra | Complete all 6 steps in search | Reviewed catalog LLM search API.
| Bhavya | 1. Complete R&D on new search logic and live sharepoint search process and tools. 2. Later submit Architecture, requirements, WorkFlow, PainPoints, and Walkthrough.
| G jama | 1.Improvements on core logic 2.analysis on transcripts of 911 calls metadata | 1.created a sheet of project end to end flow 2.created techstack sheet 3.analysied emergency calls for questions they ask | implement db's for all that non-emergency's
2026-08-14
| indra | 1. Review chat component. 2. Merge contracts & Files into Existing search.
| G Jama | implement db's for all that non-emergency's change nyc to boone county data research | done db implementation found boone county rules what questions ask either emergency or non emergency | change nyc to boone county

## Daily Activities
DATE | Name | Action Item's for the day | Status of the work | Planned Work For Tomorrow | Remarks
22/06/2026 | G Indra | Today's work centered on resolving critical platform bugs, enhancing search capabilities, and advancing DevOps and AI infrastructure for the Enterprise project. Major milestones included successfully fixing job link sharing on the Unanu USA job board, building a comprehensive knowledge base across 18 repositories, and progressing on automated testing and Azure deployment agents. Completed Tasks • Unnanu USA Job Board: Successfully resolved two specific issues related to job link sharing functionality (repo unnanu-jobs-2026). • Catalog Search Enhancement: Regenerated the catalog and successfully integrated the new intent query logic. • Enterprise Knowledge Base: Built and compiled a complete knowledge base covering all 18 repositories within the Unnanu Enterprise project. • Testing & Deployment Agents: Conducted a dry run of the new Testing Agent. Performed further testing and updates on uat.jobs.unanu.com. Worked on the deployment agent, enabling the capability to deploy any repository directly into Azure |  | Complete Testing Agent: Run the testing agent across the job portals to identify issues & Bugs. Coding Agent : It will take input from exception log table and fixes those exceptions. Finalize Deployment Agent: Complete the deployment agent to ensure any repository can be smoothly deployed to Azure. Handover to Sachin: Hand over the finalized deployment agent to Sachin for deployment on Unnanu.com. Solve Public Link Sharing: Investigate and find a solution to make the "match job link" shareable with the public. Evaluate DIR Web Search: Analyze the pros and cons of the currently implemented DIR web search logic specifically for public link sharing.
| G bhavya | 1. Shared ngrok link to hemanth for testing. 2. Started building SPFx package to integrate our search project to Sharepoint site. | Almost to finish the package. | 1. Should finish end-to-end package 2. Integrate the built package into sharepoint. 3. Work on accuracy of search
| Tapasya | On Leave | N/A
| B Sai | Completed project documentation, writing up the work done across the projects. Also fixed several UI issues in Unnanu India. | Everything is done this are docuemnts https://drive.google.com/drive/folders/1ahnj7CYYZM-x2h-XfR74LhEzA7gWZ4LX?usp=sharing | Instagram Marketing Posting Agent "I want to build an automated agent that creates and publishes marketing content to Instagram. The agent should generate captions, select relevant hashtags, schedule posts at optimal times, and post images or videos automatically. It should support campaign-based posting, maintain brand tone and voice, and track engagement metrics like likes, comments, and reach after posting."
| G jama | comparing attetnions of llama 3.2 1 b and qwen 3.2 0.5b param models how each generation of new token how much attention would pay that context(instructions,data,query) | i figure out this 2 models attentions different weights(percentages) in different tokens | selecting llm which is well train on what data we preprocessing
23/06/2026
| Bhavya | Successfully resolved configuration and build errors during the SPFx packaging process. The package has been stabilized. | Done building the SPFx package to integrate into sharepoint | 1. Have to make sure the package is perfect without any issues. 2. Should work on results of sharepoint search as they we're not accurate and should figureout a way. 3. Autocomplete is showing up for hemanth with ngrok link but it is working fine for me with the same link. Should check on it and make it works.
| Tapasya | On Leave | N/A
| Sai b | Today, I am working on generating AI videos to post on Instagram, Facebook, and YouTube. I am still refining the process to ensure the most accurate results | I have already moved past the brainstorming and initial generation phase. I am currently in the iterative process adjusting prompts, editing frames, or fixing glitches to ensure the final video meets high-quality standards before it is published | I will work on the same thing,posting the video on the social platfroms using the agents .
| G Jama | searching llms | I did't find any good for that DIR DATA | working in that dynamic creation of prompts for generating data for preprocessing and keep on searching llms
24/06/2026
| Bhavya | On leave | N/A | 1. Have to make sure the package is perfect without any issues. 2. Should work on results of sharepoint search as they we're not accurate and should figureout a way. 3. Autocomplete is showing up for hemanth with ngrok link but it is working fine for me with the same link. Should check on it and make it works.
| Tapasya | Woked on Related links feature for PMCS search | Ongoing
sai b
| G jama | working in Customer profile , how to create it | i figure out Customer Profile may help us to generate data | Working more about Customer profile, ICP(Ideal Customer Profile)
25/06/2026 | Indra
| Bhavya | Attended Mahendar's Marriage | N/A | 1. Have to make sure the package is perfect without any issues. 2. Should work on results of sharepoint search as they we're not accurate and should figureout a way. 3. Autocomplete is showing up for hemanth with ngrok link but it is working fine for me with the same link. Should check on it and make it works.
| Tapasya | Attended Mahendar's Marriage | N/A
| Sai b | Attended Mahendar's Marriage | N/A
| G jama |  | N/A | Working more about Customer profile, ICP(Ideal Customer Profile)
26/06/2026 | Tapasya | Woked on Related links feature for PMCS search | Done
| Bhavya | 1. Did R & D on integration of package into sharepoint and worked on autocomplete which is not fetching in ngrok link. | Ongoing | 1. Should work on search part as results are as accurate as before. Have to find the issue and make sure search works fine.
sai b
| G jama | about ICP difference between that Customer profile | know about ICP | working on data profile
Week completed
29/06/2026
| Bhavya | 1. Fixed search results accuracy issue. 2. Continues testing sharepoint integrateUS search and trying to resolve the issues raised by the hemanth 3. Studying Rajeev sir's code and techniques | Done | 1. Should work Groq API for LLM calls for search 2. Continuous test the site and make it as accurate as possible 3. R&D on cost efficient LLM calls and try to reduce no.of tokens for each search
| Tapasya | Working on improving chat result in PMCS search | ongoing
| G jama | Working on data profile ans understanding about documents to write my own profiles | know about data profile | write my own profiles and cross check with lllms
30/06/2026 | Bhavya | 1. Figured out a way to find issue and tested with same query multiple times with same model 2. Generated a report of the exact issue what is happening and discussed with the officials, got insight to work on LLM API's 3. Tested rajeev sir's PMCS search application and comapring with the MVP, so to improve the new things into existing IntegrateUs sharepoint search. |  | 1. First go through every step of the code to analyze where to reduce LLm calls and think if it can be fixed atleast for things 2. Get Groq API from Indra to make sure search works fine 3. Keep on testing with unique questions to improvise search
| Indra | 1. Fixed AZure complainces on app service & Databases 2. Analysed the Metadata Generated by Three different models (gpt5.4-mini ,claude-haiku-4.5 , llama-70b)
| Tapasya | Working on improving chat result in PMCS search Working on related links feature | Done | should Work on showing topic related to question in the top from result
| G jama | in that generations of llm data is not structure and they follow every time different structure with same input same model | we figure drawback is wwe can't define structure because there are so many different types of data | i write my own abstract,summary,topics,intent queries of a document and i do cross check with different models which absolute match our writings
2026-01-07 | Indra | Today Action Items :- 1. Complete the possible Complainces fix in Storage 2. Document Storage account complainces fix which needs review 3. Networking diagrams of Each product & Each services 4. Run the Pre-process on the metadata with 3 different models 5. Find out IVR project issues 6. Fix the issues in IVR project issues. 7. Complete the routine coding agent (Mac Mini US )
| Bhavya | 1. First go through every step of the code to analyze where to reduce LLm calls and think if it can be fixed atleast for things 2. Get Groq API from Indra to make sure search works fine 3. Keep on testing with unique questions to improvise search | Still have to R&D to get accurate results and to reduce LLM calls. | 1. Should get API from Indra to test the logic 2. Should check alter models for llama 70b
| Tapasya | Working on showing topic related to question in the top from result | Done | develop the live data tracking and adding to preprocessing(metadata) looping
| sai b | I am working on the instgram agent | I am currently double-checking everything to ensure all components are correct. | CI/CD Integration document for the each product using Azure devops
| G jama | i check with different models with my own writings like gemini 3,gpt 5,grok model in that i choose only that google ai studio with temprature is 0 | in that public models have temprature range is in 0.8 to 1 that's leads to we get different results and in that temprature in 0 model i get different results it did't match with my answers | i wanna do prompt refinement and check generation which is better dependence or independence nothing but individual generation or all generations in at a time (abstract,summary,intent queries,topics,titles,...)
2026-02-07
| Bhavya | 1. reolve ngrok issue 2. Make sure search works fine with current logic 3. Document everything till now 4. Test the search with the existing llama model with the new API from Indra | 1. Ngrok issue resolved 2. current logic is working perfect 3. Testing is working perfgood with the | 1. Should complete the document 2. Should check for the alternative models for Llama model 3. Work to bring the narrative part before the source doc.First give the answer of the question then show the source doc.
| Tapasya | develop the live data tracking and adding to preprocessing(metadata) looping working on search related results | Ongoing | Documentation
| sai b | The Instagram agent is done | Agent is done | I need the credentials of social media platforms
| G jama | i do prompt refinements and tried with individual generations getting different results and tried with few shot promptings | some get accuracy 30% ,50,70% with generic prompts , getting good results in few shot prompting but not sure 80% in same prompt getting some times 40%,50% that like around average 60% | working on how to create a schema for data
2026-03-07
| Bhavya | 1. Should complete the document 2. Should check for the alternative models for Llama model 3. Work to bring the narrative part before the source doc.First give the answer of the question then show the source doc. | 1. Documentation done 2. Remaining in progress 3. Tested rajeev sir's PMCS search and shared the report on results. | 1. Continue to complete the narrative answer part in search
| Tapasya | Working on Documentation | Done | Research and Documentation on search packaging
| sai b | I was awaiting for the credentials to integrating the social media platfroms for the digital marketing | pending | I need the credentails of unnanu india social media platforms
| G jama | i tried to create that schema | drawback i stuck in how handle different data, i tried but i get a long structure means 2 distnict doc getting different fields | now doing with modules create modules and trigger that modules whenever that data has this modules
2026-06-07
| Tapasya | Research and Documentation on search packaging update with PMCS latest repo , work with indra | Done documentation | update with PMCS latest repo , work with indra
| Bhavya | 1. Work on the summary of results before showing docs. | Code broke when implemented changes | 1. Fix the broken code and work on summary and percentages of accuracy of the result.
| sai b | Working the email extractor to send the mails for the unnanu india pramotions | Doing R&d | still working on R&d
| G jama | working in modules in that modules are to be dynamic to trigger baased on that data | drawback is that modules must be correct like any writings in that modules play's crucial roel in generation | work in schema , creating a schema
2026-07-07
| Indra | 1. Preprocessing of DIR Web content on using 3 different models ( Claude-haiku-4.5 , GPT5.4-mini , Llama-70B-versatile) 2. Build catalog on PReprocessed data 3. Preprare 100 Golden set questions using claude code to evalute search
| Bhavya | 1. Fix the broken code and work on summary and percentages of accuracy of the result. | done but it is not showing up correct section from where it got the answer. | 1. Work on percentages of the result accuracies in autocomplete. 2. Manually check autocomplte questions to make sure results are 100% correct.
| Tapasya | update with PMCS latest repo , work with indra | in progress(due to merge conflicts delayed) | update with PMCS latest repo , work with indra
| sai b | Still working on the email extraction from the recruting platforms | pending | still working on it
| G Jama | i created schema for docs with generic prompts , getting good results for small docs if data is large then schema would be broken | in that schema prompts should be good enough to create correct schema | create a doc everything related to process to schema creation
2026-07-08
| Indra | 1. Improved User intiuitiveness in DIR web search. 2.
| Bhavya | 1. Work on percentages of the result accuracies in autocomplete. 2. Manually check autocomplete questions to make sure results are 100% correct. | Autocomplete verification is done | 1. work on duplicate results 2. work on result percentages
| sai b | 1. I check the all the other platforms like Indeed, naukari,and all recruting platforms but there is no chance to extract the recruiter emails from the indeed and the nakuri platforms. | I was looking in to the another source to get the emails. | working on the linkedin for the emails.
| Tapasya | update with PMCS latest repo , work with indra | Done | start working on live changes
| G jama | i created doc approach of the preprocessing | in that first step i stuck in prompts how to tell an llm to generate a data profile, like how structure is it | consider one orgnaization documents and based on that organization data tell them create a data profile
2026-07-09 | Tapasya | started working on live site changes got access to pmcs admin analyzing and search query tracking | Done | Work on managing newly added , updated , deleted data
| Indra | 1. Frontend IVR PMCS logo is fixed 2. Azure Search Index issue is fixed in IVR
| Bhavya | 1. work on duplicate results 2. work on result percentages | on progress | Should fix the code and work on the duplicates
| sai b | Yes linedin is having the emails on there profiles i was trying to exract the emails from the linkedin | Pending | I want to R&D on the tools to extarct the emails from the linkedin
| G jama | i consider jira organization dataset and write prompt for creating a data profile for this documents in perplexity | in that it gives a structure , if give that structure to any llm it should follow that structure only and getting good results | working on different organizations structures in ragbench data set
2026-07-10 | Tapasya | Work on managing newly added , updated , deleted data | In progress | continue
Indra
| Bhavya | Should fix the code and work on the duplicates | on progress | Work on duplicates and test the accuracy of the narrative answer to the user
| sai b | I am working on the extracting the emails from the likedin using the google x-ray and the dom extraction | pending | Working on the linkedin Email extraction using the Dom
| G jama | consider that hubspot and create a structure of that hubspot internal data | i create a structure for that hubspot data | working with how that ragbench dataset were created
2026-07-13
| Indra | 1. List down completed and pending components in unnanu portal + customer Portal DEployment. 2. Verify the accuracy of DIR-WEB search with 100 Golden set eval 3. Verify pipeline scripting once and list down all the cons in it. | 1. Improved AI synthesised answer more intuitevely in DIR - WEB Search. 2. Citation deep linking enabled, need to test tomorrow 3. Audited child links are failing, need to fix 4. There are 5 queries which i tested , failed , debugged the trace of the each query ( catalog gap found , fixed and pushed ) Feedback Required :- 1. Rajeev P Nair Please test with your custom questions on https://azapp-websearch-uat.azurewebsites.net/ | 1. Verify citation deep linking 2. Fix Child links pre-process and metadata enrichment for child links (files and pages) 3. Find the pending & Completed components in both unnanu and customer portal.
| Bhavya | Work on duplicates and test the accuracy of the narrative answer to the user | Accuracy is good | 1. Should work on duplicates
| sai b | I am working on the linkedin email extraction from the linkedin using the dom |  | still I need to work on the linkedin extraction
| Tapasya | Work on managing newly added , updated , deleted data | In progress | Implement Answer card in PMCS search
| G jama | finding different instructions of llms based on that particular organizations | Understanding different instructions of different organizations | finding how that enreprise rag data is generated dynamically
2026-07-14 | Tapasya | Implement Answer card in PMCS search | Done | Live sync with data
| Indra | 1. Verify citation deep linking 2. Fix Child links pre-process and metadata enrichment for child links (files and pages) 3. Find the pending & Completed components in both unnanu and customer portal. | 1. Deep citation link completed, need to improve on the exact pointing out at answer. 2. Listed down all the pending components in search project. | 1. Design the Doc , Video , Audio , Image , Web processing 2. Work on When v/s how
| Bhavya | 1. work on autocomplete narrative script 2. Work on duplicate files of sharepoint | on progress | 1. work on autocomplete narrative script 2. Work on duplicate files of sharepoint 3. Work on sections part to avoid duplicate titles for the sections displaying in the frontend. 4. Discuss with the team about integrating our search to sharepoint app. 5. Preview of each file should take that particular section pages in the front-end
| sai b | I am working on the bids |  | I need work on the slack issue
| G jama | i work on enterprise rag data oynx company | they generated using 3 rules prompts,agents.md,schema based on this they created fields | how this helps to consistency to created structure data
2026-07-15 | Tapasya | Metadata sync ( 10 mins) Catalog build (1 hr) | Implementation Done
| Indra | 1. Design the Doc , Video , Audio , Image , Web processing 2. Work on When v/s how 3. Deploy LLM on mac mini 4. Discuss Microsoft defender problems with sir | 1. Qwen3.5-9B-4Bit model loaded and available. 2. Drafted Sprint planning added priorities. 3. Prepared Dataset to evaluate Data coverage. 4. Validated gold eval set and ran againist v2. | 1. Discuss and list down Micorosft Defender Problems with Nageswarsrao Nannapaneni. 2. Work on When v/s How. 3. Design the Doc , Video , Audio , Image , Web processing. 4. Finalise the priorities on Sprints tasks and start working one by one.
| Bhavya | 1. work on autocomplete narrative script 2. Work on duplicate files of sharepoint 3. Work on sections part to avoid duplicate titles for the sections displaying in the frontend. 4. Discuss with the team about integrating our search to sharepoint app. 5. Preview of each file should take that particular section pages in the front-end | 1. Autocomplete narrative script is working fine. 2. Preview of sections into particular page of the section is done. | 1. Work on duplicate files of sharepoint 2. Work on sections part to avoid duplicate titles for the sections displaying in the frontend. 3. Discuss with the team about integrating our search to sharepoint app.
| saib | I am working on the bids |  | I need to work with kavitha for unnanu india
| G jama | how this helps to consistency to created structure data and how it helps unnanu_preprocessing stage | i figure out they follow different structure based on that data(Oynx) | using that prompts i am gonna consider one enterprise organization then create metadata for that organization
2026-07-16 | Tapasya | Working on : new -> Created date updated -> last updated delete -> make it inactive or flag it | In Progress
| Bhavya | 1. Work on duplicate files of sharepoint 2. Work on sections part to avoid duplicate titles for the sections displaying in the frontend. 3. Discuss with the team about integrating our search to sharepoint app. | 1. Section title duplicates should be resolved while preprocessing 2. Resolved the issue of duplicate section titles to the extent can be done. 3. Worked on packaging of the search to integrate into sharepoint | 1. Build the ready to integrate SPFx package 2. Work with hemanth credentials to integrate the package into sharepoint.
| Indra | 1. Discuss and list down Micorosft Defender Problems with Nageswarsrao Nannapaneni. 2. Work on When v/s How. 3. Building Query authored Lane V3 ( comparison of v1 vs v2 vs v3) 3. Design the Doc , Video , Audio , Image , Web processing. 4. Finalise the priorities on Sprints tasks and start working one by one. | 1. Comparison betweem RAG v/s wieghted lane done. 2.Built SQL Authored Query Lane. 3. Generate comparison report | 1. Deploy Qwen-3.5VL 2. Work on solutioning of prioritising the tasks
| saib | I am working on the slack isuue |  | I need to check the issue of auto jobposting
| G Jama | using that prompts i am gonna consider one enterprise organization then create metadata for that organization | i created a system instructions of Unnanu_slack messages | Create a company ,data,audience profile dynamic not generic
2026-07-17 | sai b | i am working on the slack issue and the auto jobposting issue | Auto job_posting is done | I need to work on the slack, bids
| Bhavya | 1. Build the ready to integrate SPFx package 2. Work with hemanth credentials to integrate the package into sharepoint. 3. Document process of integration idea. | Deployed Sharepoint search package into IntegrateUS home page | Should get insights and work on improvisation
| indra | 1. Deploy Qwen-2.5VL 2. Work on solutioning of prioritising the tasks 3. | 1. Deployed 2.5 VL - 7 B - Instruct
| Tapasya | Working on : new -> Created date updated -> last updated delete -> make it inactive or flag it
| G jama | Create a company profile dynamic not generic | created a company profile based on the file it is static fields but more sub fields | work on execution how that comapny profile helps
2026-07-20
| Indra | 1. Run Evaluation tests on Rajeev sir logic. 2. Generate Catalog and autocomplete using Fable 3. Integrate Customer Portal and Search Project Deployment portal. 4. Verify PMCSServices domain certification. | 1. Ran evaluation test on Rajeev sir logic and given feedback on evaluation test 2. generated catalog and autocomplete using fable. 3. PMCS domain verification done. 4. Understanding the CSP and listed down the gaps for demo. 5. KB with harshith.
| sai b | I am working on the slack and bids | 1. the slack issue is done and bids also done | work on the resume chat bot
| Bhavya | On Leave | - | -
| G jama | work on creating different company profiles based on requirement | 1.create profiles based on website data and examples of past created(fewshot examples) with different models 2. write system prompt for profile creations ex pMCS,amazon 3.i validate amazon it writes good profile | 1.create workflow for profile creations 2.model selection
| Tapasya | Worked on Extending metadata sync and catalog rebuild time | Done
2026-07-21 | Bhavya | On Leave | - | -
| Indra | 1. List down pending modules for Demo 2. Improvements of Eval Dataset 3. Implementation design draft for CSP | 1. List down pending modules for Demo 2. Improvements of Eval Dataset 3. Implementation design draft for CSP
| sai b | working on the resume chatbot | Pending | I need to work on the resume chatbot
| G jama | 1.create workflow for profile creations 2.model selection | 1.created a profiles in 6 companies 2. tries with gemini ,chatgpt,claude models | create a detailed report try with different companies
| Tapasya | Implemented the Search Questions tracking with latest updated data in backend with query type SearchTapasya | Done | Prepare a Single pager for PMCS search+chat work on how to package search for unnanu or any other website
2026-07-22 | Bhavya | On Leave | - | -
| indra | 1. Implement One-Pager for Entire search Product. 2.Implement DATA connector for mysql. 3. Implement Discovery Phase of Mysql. 4. Wrap Website Processing with REST API's . 5. Run & Validate processing Pipeline. | 1. Implemented one-pager. 2. Completed Azure resource inventory Mapping of MVP!,MVP2,Enterprise Search.
| Tapasya | Prepare a Single pager for PMCS search+chat work on how to package search for unnanu or any other website | Done | 1. Worked on CronJobs (metadata and catalog) 2. going throught customer deployment process in customer portal project
| sai b | working on the resume chat bot and bids | pending | Still working on the resume chat bot
| G Jama | create a detailed report try with different companies | 1.created different domains comapnies (different industries with same DIR is example) 2. add meta thinking model 3. after reading of that responses i get all were giving good | make a detailed report with different models
2026-07-23 | Tapasya | 1. Worked on CronJobs (metadata and catalog) 2. going throught customer deployment process in customer portal project | Done | Work on issues
| indra | 1.Complete Azure Resouce Inventory Mapping. 2. Include Hybrid Search in one-pager comparison. 3. Make IVR Storage account access throgh API by making private containers. 4. List Down all the services uses unnanu Storage acccount. 5. Test and validate CSP Demo on website processing. | 1. Except miscelleneous ARIM done. 2. Fixed. IVR storage complaince. 3. MySQL Data connectors done. 4. Listed down the services using unnanu.
| Bhavya | 1. Should work on Security Level permissions of Sharepoint for access. | In progress | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Should update on changes made in the documents 4. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs 5. Give one-Pager of AI Search for IntegrateUs Sharepoint.
| sai b | working on the resume chatbot | in progress
| G Jama | make a detailed report with different models | created a detailed report | Analysis of reports generated by bots
2026-07-24 | Tapasya | 1. Encountered few issues on Website search and solving 2. working on onepager(prompt shared by rajeev) | Done | Work on architecture of search
| indra | 1. Discuss the Storage account identity based approach with mahender. 2. Introspection eval-2 dataset , list down pros and cons of dataset. 3. Implementation of Discovery agent 4. Integrate discovery agent to Search wizard. 5. Re-ordering of Search wizard. 6. Dry-run of search wizard. 7. Remove stale / Dead code from Processing-services ( Document,Image,audio,video) 8. Fix Blob anonymous access. | 1. Drafted One pager using Rajeev sir prompt. 2. Drafted the discovery agent workflow. 3. Reordering the workflow. 4. Confirm that the wizard’s reordering is correct. 5. Remove any remaining dead code from the four processing services, including document, image, and audio/video. All four processing services are complete.
| Bhavya | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Should update on changes made in the documents 4. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs 5. Give one-Pager of AI Search for IntegrateUs Sharepoint. | 1. One pager is done and delivered to rajeev sir. 2. Document updation done | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs
| sai b | i am working resume chat bot and the bids
| G Jama | Analysis of reports generated by bots | 1.getting contrdiction results 2.finally better to introduce human evoulation | 1.Try with API keys of everything
2026-07-27 | Tapasya | 1. Draw Architecture for PMCS website search (insights taken from nagi sir on friday) 2. researching on Search packaging | Done | test search on live data
| indra | 1. Deploy Llama 8B in mac-mini -Rajeev. 2. Fix all three compliance items for the 1.0 Storage Account. a. Restrict App Service access to a selected public network. b. Blob anonymous access is disabled. The task is complete, but the Talent Web App raised an exception; Mahinder will investigate. c. Rotation key: Mahinder is using a different ID. After he updates the code to the Anthropic ID, we will need to address each rotation individually. 3. Search Project wizard status. 4. Introspecting of Eval-2 dataset. - Hold 5. Where am i on the accuracy phase. | 1. Need confirmation from saib@unnanu.com to disbale Oauth Client secret. 2. Successfully deployed the 8‑billion‑parameter llama-3.1 LLM on the Mac mini using VLLM. 3. Blob Anonymous Access was disabled On Friday, but the TalentWeb app raised an exception. Mahendra will investigate once he receives feedback. After the issue is fixed, I will re‑disable it. 4. Regarding the rotation key, Mahinder and I worked on creating the idenity on Friday. We created an identity for the espally storage account and tested it on the p‑other API. After Mahinder completes testing, we will deploy it wherever it is used and then rotate the key. 5. Regarding public access to the storage account, we face two issues: - There is no option to enable it by resource type; for both CDN and App Services we must add it manually. - Adding the outbound component for the CDN is not feasible because the CDN is globally distributed, making it complex. The simplest solution is to use the VNet. For App Services, the VNet costs $0.01 per hour (about $7.30 per month) plus $0.01 per GB of data processed. We also need to upgrade Fendo from Standard to Premium to enable this. 6.
| Bhavya | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs | 1. Worked on permissions of accounts in sharepoint but still needs to be verified and did R&D on how to loop the search for all files integration | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs
| sai b | I working on the bids , resume chatbot | Bids are done, chatbot is still pending | Continue working on the resume chat bot
| G Jama | 1.Try with API keys of everything | 1.I selected models 2.did't understand completely about thinking of a model | 1.learn more about thinking levels 2.select which model to enable how much thinking level 3.after selecting generate data
2026-07-28 | Tapasya | 1. PMCS website is updated with new blog data , so testing live search 2. work on search issues 3. work on repo updation | search issues and testing still in process | 1. Re-do the one-pager for PMCS 2. Gain knowledge on SEO,GEO, AEO 3. work paraprasing issue
| indra | 1. Preapre workflow of the branch protection settings. 2. Take screenshots for Evidence collection. 3. List down all backups we have,need to have. | 1. Collected Evidence for branch protection. 2. Workflow is prepared for branch protection reviewd with Nageswarsrao Nannapaneni .
| Bhavya | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs | 1. fetched permissions of each document level into database and should make it better for our next pipeline | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs 4. Re-do the one-pager for sharepoint search.
| sai b | I am working on the resume chat . | pending | Continue working on the resume chat bot and n8n workflow
| G Jama | 1.learn more about thinking levels 2.select which model to enable how much thinking level 3.after selecting generate data | 1.i selected models but in benchmark datasets they are not good 2. In thinking level selection MAX to everything ,because generate once only that profiles | 1.based on becnchmark datasets consider models which are top performances 2.if they are reasoning models enable it max
2026-07-29 | Sai b | I am working on the resume chat bot and n8n workflow,bids | Resume chatbot was done and i was testing the chatbot,i n8n workflow is pending,bids are pending | I need to work on the bids, resumechatbot and n8n workflow
| Tapasya | 1. Re-do the one-pager for PMCS 2. Gain knowledge on SEO,GEO, AEO 3. Work paraprasing issue
| Indra | 1.Complete the changes mentioned by Madhu for the DIR one‑pager. 2. Prepare the infrastructure requirements and prerequisites for deploying the website search to the client. 3. Prepare an outline of all tasks needed to deploy the entire search product to the client, including dates and due dates. 4. Prepare a backup and recovery sheet by environment and product. 5. Prepare the action items for completion of Search Product. 6. List all the delegate action items. 7. Test Disabling anonymous access | 1.Completed the backup and recovery sheet by environment and product, and sent it to the NNR for review. 2. I completed the changes Madhu requested for the DIR One pager and sent the required email to Madhur,Rajeev and NNR. 3. Completed two compliance tests: 1. Anonymous blob access for the Unnanu storage account 2. Allowing public traffic for the SQL board Both are completed. 4. Action items are prepared, and an outline of all tasks with due dates for the product has been created.
| Bhavya | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Draw end-to-end architecture of the Sharpeoint search of IntegrateUs 4. Re-do the one-pager for sharepoint search. | 1. Re-do of one-pager done. Waiting for review 2. Discussed with Jama regarding model evaluation and trying to validate the best model for generating data profiles. 3. End-to-end architecture is done 4. Worked on full fledged sharepoint search | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint
| G Jama | 1.based on becnchmark datasets consider models which are top performances 2.if they are reasoning models enable it max | 1.create a dataset fields 2.domain adaption is primary concern for any profile | 1.understand problem statement of Automated AI Non-Emergency Call Triaging System 2.Existing System reference 3.proposed System
2026-07-30 | Bhavya | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Working with Jama to evaluate best model to generate data profile. | 1. Done with the one-pager | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Working with Jama to evaluate best model to generate data profile. 4. Re-do the One-pager
| Indra | Search : - 1. Prepare the infrastructure requirements and prerequisites for deploying the website search to the client. 2. Complete today’s action items for the product. Complainces :- 1. Create an Azure architecture diagram for the Automated AI Non-Emergency Call Triaging System | 1. I've completed the infrastructure requirements and the preview quizzes for the website search product. 2. In the Searc project action items were completed during the 30th activities. 3. Created an Azure solution architecture diagram and an Azure resource diagram for the non‑emergency call‑tracing system.
| sai b | I am working on the bids and the resume chatbot | so the resume chatnotwas done and i was testing with the queries,bids are also done | I need to work on the resume chatbot and the n8n workflow and linkedin chrome extension
| Tapasya | 1. Continuing testing PMCS search 2. Working on paraprasing 3. Working on updating One pager | Done Updating one pager | 1. Continuing testing PMCS search 2. Working on paraprasing
| G jama | 1.understand problem statement of Automated AI Non-Emergency Call Triaging System 2.Existing System reference 3.proposed System | 1.understand problem statement 2.understand Existing System 3.understand what that boon countey do 4.Understand proposed System | 1. go through proposed architecture 2.Understand more about Problem statement 3.Go through proposed Dataflow
2026-07-31 | Bhavya | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Working with Jama to evaluate best model to generate data profile. 4. Re-do the One-pager | In progress, one-pager done | 1. Continue working on the Permission levels. 2. Implement search for all the files of IntegrateUs sharepoint 3. Working with Jama to evaluate best model to generate data profile.
| Tapasya | 1. Continuing testing PMCS search 2. Working on paraprasing 3. Update one pager | Updated One pager and sharing word document to madhu and rajeev
| indra | 1. Complet the Search project action items for the 31st. 2. | 1. Completed the project action items for the 31st.
| sai b | 1. I am working on the n8n automation of the montly transcrpit. 2. resume chatbot 3.Linkedin chrome extension. | 1. N8N automation is completed 2. resume chatbot is completed we need to test it. 3. Linkedin is pending | 1. go through on the linkedinextension and the resumechatbot.
| G Jama | 1.Understand more about Problem statement -> about what actually BCJC is ->what are the Examples of BCJC calls ->what BCJC problem | 1.understand BCJC services 2.read some examples of BCJC calls 3.Understand problem | 1. go through proposed architecture 2.data analysis of 311 emergency data 3.build a knowledge base

## ToolsAccess
Name | Paid Tools / Softwares | Login / API | Access Granted | Purpose | Remarks
sai b | Groq LLM | API | YES |  | It is for the auto document formatting and auto job posting
sai b | SEND GRID | API | YES |  | It is for the unnanu.in mails
sai b | GEMINI LLM | API | YES |  | It is for generating LinkedIn posters and Instagram agent to create videos and images for marketing.
sai b | FIREFLIES | LOGIN/API | YES |  | It is for the auto uploading to the drive to store the daily meeting files
sai b | AZURE DEVOPS | LOGIN | YES |  | It is for managing project workflows and source code repositories and managing the development pipeline.
sai b | INSTAGRAM,YOUTUBE,LINKEDIN,FACEBOOK | LOGIN/API | NO |  | Marketing for the Indian jobboard
Bhavya | Groq LLM | API | No | Search
Bhavya | DataGrip | Login | Yes | Tracking search | For storing data of preprocessed files and to track the working of the application
Bhavya | Azure App Integration | Login | Yes | Authentication | To authenticate and fetch sharepoint files
Bhavya | Claude | Login | Yes | Coding | For implementation and R&D
Tapasya | Groq LLM | API | Yes | For Preprocessing and Generating Data Tables | Using llama-3.3-70b-versatile via Groq API provided by indra for Preprocessing data and Generating Metadata ,Catalog, Autocomplete Tables
Tapasya | Claude | Log in (helloclaude@unnanu.ai and unnanu@unnanu.ai(currently using)) | Yes | Coding | For Develoment
Tapasya | Azure PMCS Datastorage | Login (access given by indra to tapasya@unnanu.com) | Yes | Data read access for implementing search in PMCS Website | For developing search
Tapasya | PMCS admin page | Logged in (with madhu account) |  | for checking live search and data history | search tracking and improvements
Tapasya | PMCS Sharepoint | Logged in (with suman account) |  | For accessing Sharepoint files | used for accessing sharepoint files through code
G jama | Claude | Log in (helloclaude@unnanu.ai) | yes | document creation
saii b | Azure log access for the resume chatbot(uat and prod) | Log in | no | I need to check the logs for the issue | I need it for the logs to find the issue.

## Boon county non_emergency handl
Action Items | Sub Tasks | Status | Due Date | Assigned To | Reviewer | Review By | Note | Tools/languages/frameworks/chatbots/websites | Modifications
Collecting dataset from boon's county non emergency calls for classification. |  | pending | 2026-08-03 | jama & harshith | indra and NNR | indra , NNR,rajeev | using internet found data | 1.perplexity (bots) 2.gemini (bots)
| found NYC Metadata both emergency and non-emergency | completed | 2026-08-04 | jama & harshith | indra and NNR | indra , NNR,rajeev |  | NYC Opendata website
research on metadata fields which are mandatory to ask and how they elaborate based on that fields |  | pending | 2026-08-12 | jama & harshith | indra and NNR | indra , NNR,rajeev
| emergency data fields | ongoing | 2026-08-13 | jama & harshith | indra and NNR | indra , NNR,rajeev | Collect the data fields | claude model
| non-emergency data fields (service,info) | pending | 2026-08-14 | jama & harshith | indra and NNR | indra , NNR,rajeev | Collect the data fields | claude model / any other models or techniques
Analyse and visualization of Non-Emergency Datset |  | pending | 2026-08-03 | jama & harshith | indra and NNR | indra , NNR,rajeev
| analysis on collected data | ongoing | 2026-08-13 |  |  | indra , NNR,rajeev | do analysis on what data fields they ask {ETC}. And how they elaborate based on those fields | claude model
| visulized complaints of non-emergency data of NYC | completed | 2026-08-04 |  | indra and NNR | indra , NNR,rajeev | 1.Using nyc open data website perfomed visulizations | NYC opendata visulization tool
Build knowledge base for responses (ground truth) |  | pending | 2026-08-04 | jama & harshith | indra and NNR | indra , NNR,rajeev
| either vector embeddings or our unnanu search discuss with team and conclude | pending | 2026-08-14 |  | indra and NNR | indra , NNR,rajeev | chunks(semantic/unnanu technique) | 1.vectordb 2.unnanu technique(tables)
build a intent classification tecnique to give responses and handle responses to non-emergency calls (algorithm) |  | pending | 2026-08-05 | harshith and jama | indra and NNR | indra , NNR,rajeev
| build logic of classify and select category and ask that category slots to fill service request | completed | 2026-08-10 |  |  | indra , NNR,rajeev | Using slm/llm/ml algorithms | 1.Using groq inference (llama 3.1 8b model)
| add handle understand of addresses names | pending | 2026-08-17 |  | indra and NNR | indra , NNR,rajeev | 1.research on how they check addresses 2.based on that learn how to automate that place addresses identify correctly 3.giving llm to common sense | perplexity bot,nyc opendata website,claude model
build logic of emergency detection and trigger to telecommunicator |  | pending | 2026-08-17 | harshith and jama | indra and NNR | indra , NNR,rajeev |  | 1.Using groq inference (llama 3.1 8b model)
| build a system for emergency detection | completed | 2026-08-11 |  |  | indra , NNR,rajeev | works should predict wheather it is a emergency or not | via llm prompt's to we classify
| buid robust system | pending | 2026-08-17 |  | indra and NNR | indra , NNR,rajeev | 1. don't miss if it is in service/info request turns 2. research on how well to describe to llm | via llm prompt's to we classify
build a SIP/voip communication System and integrate with developed technique |  | pending | 2026-08-06 | harshith and jama | indra and NNR | indra , NNR,rajeev | using python frameworks | python framworks
| ACS(Azure Communication Service) | pending |  |  |  | indra , NNR,rajeev
| try twillo has alternative | pending |  |  | indra and NNR | indra , NNR,rajeev
build STT and TTS pipelines |  | pending |  | harshith and jama | indra and NNR | indra , NNR,rajeev | using any open source STT/or anyother
| find models and build a system | completed | 2026-08-11 |  |  | indra , NNR,rajeev |  | 1.Deepgram REST API nova-2 ( STT) 2.es_MX-claude-high TTS(hugging face model Speaches-ai community) -spanish 3.en_US-lessac-medium TTS( hugging face model Speaches-ai community) - english
| find least optimized models | pending |  |  | indra and NNR | indra , NNR,rajeev
build data base for call records + services request |  | pending | 2026-08-07 | harshith and jama | indra and NNR | indra , NNR,rajeev | Using azure db
| 1.DB FOR emergency metadata | completed | 2026-08-11 |  | indra and NNR | indra , NNR,rajeev |  | 1. local using sqllite
| 2.DB For non-emergency metadata | pending |  |  | indra and NNR | indra , NNR,rajeev
| 3.DB For information metadata | pending |  |  | indra and NNR | indra , NNR,rajeev
| 4.DB For audit logs | pending |  |  | indra and NNR | indra , NNR,rajeev
build dashboard |  | pending | 2026-08-13 | harshith | indra and NNR | indra , NNR,rajeev |  | using any html,css,js
| 1.Showing emergency trackings | pending |  |  |  | indra , NNR,rajeev
| 2. non-emergency trackings | pending |  |  |  | indra , NNR,rajeev
Testing |  | pending | 2026-08-08 | jama and harshith and indra | indra and NNR | indra , NNR,rajeev | create golden answers and then do testing
| create a synthetic data bsed on nyc data non - emergency | completed | 2026-08-09 |  |  | indra , NNR,rajeev |  | using llm(claude sonnet 4..6) for creating synthetic data | removed keyword search and only use llm to classify
| create a synthetic data bsed on nyc data emergency | completed | 2026-08-12 |  |  | indra , NNR,rajeev |  | using llm( gemini 3.6 flash high) for creating synthetic data
| 1.emergency or non emergency testing in every user turn | completed | 2026-08-12 |  |  | indra , NNR,rajeev | based on combine keyword + llm classification we done it | llm(llama 3.1 8b),python program
| retest with new architecture (emergency or non emergency testing in every user turn) | pending |  |  |  | indra , NNR,rajeev
sample UI for showing records of data |  | pending |  |  |  | indra , NNR,rajeev
| emergency db | completed | 2026-08-12 |  |  | indra , NNR,rajeev |  | using html,css,js
| non emergency db | pending |  |  |  | indra , NNR,rajeev
| info db | pending |  |  |  | indra , NNR,rajeev
| audit db | pending |  |  |  | indra , NNR,rajeev

## toolsframworks_boone county
Third-party packages | notes | Standard-library modules(python) | notes | languages | Notes
openai>=1.0 | OpenAI SDK is a Python library that helps your application communicate with an AI model through an HTTP API. | sqlite3 | sqlite3 is built into Python and provides access to SQLite. SQLite itself is a database engine, but your Python code accesses it through the standard-library sqlite3 module.
python-dotenv>=1.0 | load_dotenv() reads .env (gitignored) into os.environ once at process start, so the rest of the codebase can just call os.getenv(...) like the vars were always there — no per-developer shell profile setup, no secrets in source. | os(operating system) | os is a Python standard-library module for interacting with the operating system.
gradio>=4.0 | Gradio's Blocks API builds the two-pane chat + live-classification-panel tester in ~300 lines of pure Python. A Flask/FastAPI + hand-written HTML/JS front end would take far longer for what is explicitly a testing rig, not the production BCJC console. | json | json.loads() for deserializing JSON text into Python objects and json.dumps() for serializing Python objects into JSON text.
pyyaml>=6.0 | YAML over JSON/CSV specifically because it supports # comments and nested structure that non-engineers can still edit. | re(regular expression) | regex, is a pattern used to search, match, or extract parts of text.
tqdm>=4.0 | tqdm wraps the loop so a human running the eval sees live progress instead of a silent terminal | uuid(Universally unique identifier)
requests>=2.0 | It is the local Python tool that sends and receives web requests. Requests provides a higher-level interface for HTTP operations such as GET and POST
piper-tts>=1.2.0 | loads and executes the model

## Resources_of_boons_county
datasets | tools | frameworks | languages
1. collect via internet 2. 311 non emergency calls | 1. claude/perplexity for analyis of data

## PRE_Processing_activites
Assigned_date | activity | status | Reviewer | Assigned by
2026-07-27 | try with api keys | pending |  | indra
2026-07-28 | learn about thinking of a model | completed
2026-07-29 | prepare a evalution dataset for profile creations | working |  | indra
2026-07-30 | 1.after creating dataset create profiles with different models and evaluate results 2.write a evaluation report | planned

## ref-pending-search-projects
Sprint Name | Action items | Platforms | Sub Tasks | ETA
| Feat :- Unnanu Azure cloud integration for unnanu cloud. | Unnanu & Customer Portal.
| Feat : Azure cloud integration | CPD & SPD
| Feat : AWS Cloud integration | CPD & SPD
Make pre-processing pipeline for Cloud agnostic and DB agnostic
Custom Domain for deployed services
| SSO (single-sign on) Enterpise Authorisation | Customer Portal
GCP Specific
Sprint 5 - Integration & Demo Readiness | Separate Customer Portal and search project deployment | Customer Portal. | • Split monorepo into 4 repos: CP FE, CP BE, SPD FE, SPD BE; repo structure, branch strategy & dependency mapping | 2-3 days
|  |  | • Set up CI/CD pipelines for all 4 codebases across UAT & PROD | 2 hours
• Separate CP FE (Next.js) into its own codebase; update routes, env URLs, deep links
• Separate SPD FE (Next.js) into its own codebase; update routes, env URLs, deep links
|  |  | • Remove tightly coupled shared FE modules; retain only reusable components/contracts | 2-3 days
|  |  | • Separate CP BE (.Net 10) into its own codebase; reconfigure app settings, DB, auth | 1-2 days
• Separate SPD BE (.Net 10) into its own codebase; reconfigure DB, cache, queue configs
|  |  | • Split shared BE services: auth, API contracts, logging, deployment hooks, background jobs | 1-2 days
• Reconfigure service-to-service communication & endpoint management
|  |  | • Create App Service for each of the 4 repos (CP FE, CP BE, SPD FE, SPD BE) in UAT & PROD | 1 day
• Configure env variables, secrets, domains & SSL for all 4 codebases across UAT & PROD
• Set up UAT & PROD for CP FE: env configs, secrets, domains, build/release
• Set up UAT & PROD for CP BE: app settings, DB connections, API endpoints, deployment slots
• Set up UAT & PROD for SPD FE: env configs, API URLs, auth, deployment setup
• Set up UAT & PROD for SPD BE: app settings, DB/cache/queue, deployment slots
• Reconnect & validate SPD portal integrations post-split
|  |  | • End-to-end UAT testing for CP and SPD: smoke + regression | 2 days
|  |  | • PROD release checklist, rollback plan & deployment verification | 1 day
| Devops : Prepare both UAT & Prod Environments | All platforms
|  |  | • Configure app settings & env variables for all 8 repos (CP FE/BE, SPD FE/BE, UCAP FE/BE, CPD FE/BE): API URLs, auth keys, DB connection strings, secrets, feature flags - UAT & PROD | 1-2 day
• Verify all pipeline scripting for all 8 repos (CP FE, CP BE, SPD FE, SPD BE, UCAP FE, UCAP BE, CPD FE, CPD BE) across UAT & PROD
• Configure CORS policies & API gateway rules for all 8 repos (CP FE/BE, SPD FE/BE, UCAP FE/BE, CPD FE/BE) - UAT & PROD
• Enable HTTPS only, TLS 1.2+ & SSL binding for all 8 App Services across UAT & PROD
• Configure staging deployment slots & swap strategy for all 8 repos in PROD
• Set up Azure Key Vault references for all secrets across all 8 App Services in UAT & PROD
• Configure Application Insights, health checks & alert rules for all 8 App Services - UAT & PROD
| Data collection from CUstomer portal to UCAP the billing , Licensing , Activity between Unnanu Portal <---> Customer Portal | UCPA & CP | • Sync license tracking data from CP to UCAP: active licenses, plan types, expiry dates, seat counts per search project | 2-3 days
|  |  | • Sync ticketing data from CP to UCAP: support tickets, issue status, priority, resolution time per customer | 2-3 days
|  |  | • Sync activity logs from CP to UCAP: user actions, login history, feature usage, search query activity per customer | 2-3 days
|  |  | • Sync billing data from CP to UCAP: invoices, payment status, subscription plans, overdue accounts per search project | 2-3 days
|  |  | • Track search project customers in UCAP: profile, onboarding status, assigned SPD projects, active deployments | 2 days
|  |  | • Track issues via ticketing in UCAP: open/closed tickets, SLA tracking, escalation status per customer | 2 days
|  |  | • Track search project licensing in UCAP: license assignments, upgrades, renewals, violations per customer | 2 days
|  |  | • Track billing health in UCAP: subscription status, failed payments, billing cycles, dunning per customer | 2 days
|  |  | • Build admin dashboard in UCAP: consolidated view of licenses, tickets, activity, billing & search project health | 3-5 days
|  |  | • Set up API/webhook between CP BE and UCAP BE for real-time data sync across all tracked entities | 3-4 days
|  |  | • Define RBAC permissions in UCAP: Unnanu admin can view/manage all CP customer data across search projects | 1-2 days
|  |  | • Validate data sync accuracy in UAT: licensing, ticketing, activity, billing & customer tracking modules | 2 days
| Data source connectors - Storage services | SPD | • GCP Storage connector: implement Google Cloud Storage integration; auth via Service Account, bucket listing, file read/write/delete, metadata indexing | 3-4 days
|  |  | • AWS S3 connector: implement Amazon S3 integration; auth via IAM roles/access keys, bucket/prefix listing, file read/write/delete, metadata indexing | 3-4 days
|  |  | • SharePoint connector: implement SharePoint Online integration; auth via OAuth2/App registration, site/library listing, document read/index, delta sync | 4-5 days
|  |  | • OneDrive connector: implement OneDrive for Business integration; auth via Microsoft Graph API, folder/file listing, document read/index, delta sync | 3-4 days
|  |  | • Google Drive connector: implement Google Drive integration; auth via OAuth2/Service Account, folder/file listing, document read/index, change tracking | 3-4 days
|  |  | • Snowflake connector: implement Snowflake data warehouse integration; auth via key-pair/SSO, schema/table discovery, query execution, result indexing | 4-5 days
|  |  | • BigQuery connector: implement Google BigQuery integration; auth via Service Account, dataset/table discovery, query execution, result indexing | 4-5 days
|  |  | • Amazon Redshift connector: implement Redshift integration; auth via IAM/JDBC, schema/table discovery, query execution, result streaming & indexing | 4-5 days
|  |  | • Azure Synapse Analytics connector: implement Synapse integration; auth via Azure AD, workspace/pool discovery, SQL query execution, result indexing | 3-4 days
|  |  | • Dropbox Business connector: implement Dropbox Business integration; auth via OAuth2, team folder listing, file read/index, change webhook support | 3-4 days
|  |  | • Box Enterprise connector: implement Box Enterprise integration; auth via OAuth2/JWT, folder/file listing, document read/index, metadata & event sync | 3-4 days
|  |  | • SFTP / NFS connector: implement SFTP & Network File System integration; auth via SSH key/password, directory listing, file read/index, scheduled sync | 3-4 days
|  |  | • Unified connector config UI: allow customers to configure, test & manage all storage connectors from CP settings panel | 3-5 days
|  |  | • Connector health monitoring: implement connection status checks, error logging, retry logic & alerts for all storage connectors | 2-3 days
|  |  | • End-to-end testing of all storage connectors in UAT: file ingestion, indexing, search validation & error handling | 3 days
MVP 2 Development | Deployment of Preprocessing Services (Doc , Video , Audio , Image , Web) - In Cloud GPU (GCP ) | SPD | • Select & finalize open-source multimodal LLMs: evaluate LLaVA, Qwen-VL, InternVL, Phi-3 Vision, Gemma 3 for doc/audio/video/image understanding | 2-3 days
|  |  | • Set up GCP GPU instances (A100/L4/T4) with CUDA, cuDNN, Python env, Hugging Face Transformers & vLLM/Ollama serving stack | 2-3 days
|  |  | • Containerize multimodal LLM APIs using Docker with GPU runtime support; build separate containers per modality (doc, image, audio, video) | 3-4 days
|  |  | • Deploy containerized LLM APIs on GCP GPU instances using GKE or Cloud Run GPU; configure autoscaling, health checks & GPU resource limits | 3-4 days
|  |  | • Implement document preprocessing pipeline: PDF/DOCX/PPTX parsing, chunking, multimodal LLM embedding via deployed API | 3-5 days
|  |  | • Implement image preprocessing pipeline: image ingestion, CLIP/vision encoder via deployed multimodal LLM API, metadata & caption extraction | 3-4 days
|  |  | • Implement audio preprocessing pipeline: audio transcription via Whisper/multimodal LLM, chunking, embedding & indexing | 3-4 days
|  |  | • Implement video preprocessing pipeline: frame extraction, audio separation, multimodal LLM captioning per frame, temporal indexing | 4-5 days
|  |  | • Implement web content preprocessing pipeline: URL crawling, HTML parsing, content extraction & multimodal LLM summarization/embedding | 3-4 days
|  |  | • Auto-integrate deployed LLM APIs into preprocessing services: dynamic endpoint injection at runtime via config/env variables - no hardcoded URLs | 2-3 days
|  |  | • Implement IP protection & code obfuscation: compile Python preprocessing services to bytecode (Cython/PyArmor); strip source from deployed containers | 3-4 days
|  |  | • Implement encrypted config management: all LLM API endpoints, keys & business logic configs stored in GCP Secret Manager; injected at runtime only | 2-3 days
|  |  | • Ensure zero source code exposure: Docker images contain only compiled binaries; customers can access GCP instances but cannot read business logic or model routing | 2-3 days
|  |  | • Implement API gateway layer: all preprocessing service calls route through internal gateway; LLM API selection, load balancing & fallback handled automatically | 3-4 days
|  |  | • Set up GPU utilization monitoring, LLM inference latency tracking & alerting via GCP Cloud Monitoring & Prometheus | 2-3 days
|  |  | • End-to-end UAT validation: test all modalities (doc, image, audio, video, web) through preprocessing pipeline with deployed multimodal LLMs in GCP | 3-4 days
MVP - 2 Development | Feat : Integrate Web search Package on drupal | Search project Deployment portal | • Wrap core search logic into a secured REST API: endpoints for query, index, suggest & health check; no business logic exposed externally | 3-4 days
|  |  | • Build Drupal custom module (unnanu_search): installable via Composer; module connects to the search API using a configurable API URL & API key | 4-5 days
|  |  | • Implement module admin config UI in Drupal: settings page for API URL, API key, search project ID, timeout & environment (UAT/PROD) | 2-3 days
|  |  | • Implement API URL auto-injection: after customer installs the Drupal package via SPD, the correct API URL is auto-populated from their search project config | 3-4 days
|  |  | • Implement Drupal search block & search results page: renders search UI, sends queries to core search API, displays ranked results with filters & pagination | 3-4 days
|  |  | • Implement authentication between Drupal module & search API: API key validation, per-customer token scoping, rate limiting & request signing | 2-3 days
|  |  | • Package the Drupal module for Composer install: publish to Packagist or private registry; versioned releases aligned with SPD deployments | 2-3 days
|  |  | • Implement IP protection for the Drupal module: obfuscate internal API routing logic; customers can configure API URL but cannot reverse-engineer core search logic | 2-3 days
|  |  | • Implement graceful error handling in module: API timeout fallback, connection failure messages, retry logic & admin alert notifications | 1-2 days
|  |  | • Support multi-environment in module: single Drupal install can switch between UAT & PROD search API URLs from admin settings | 1-2 days
|  |  | • Write module installation documentation & auto-setup guide: step-by-step Composer install, config steps & SPD integration walkthrough | 1-2 days
|  |  | • End-to-end UAT testing: install module on test Drupal site, configure API URL, run search queries & validate results against core search API | 2-3 days
Pilot Release Readiness | Feat : Integrate Sharepoint search | SPD | • Build SharePoint Framework (SPFx) Web Part as a custom search experience: React-based search UI embedded natively inside SharePoint pages | 4-5 days
|  |  | • Implement Azure AD OAuth2 authentication in SPFx app: tenant-level app registration, consent flow, token acquisition & per-user scoped access | 3-4 days
|  |  | • Implement API URL auto-injection: after customer connects search project via SPD/CP, the correct search API URL is auto-configured in the SPFx app settings | 3-4 days
|  |  | • Integrate SPFx app with Customer Portal search API: send user queries to CP search API endpoint, receive & render ranked results with filters & pagination | 3-4 days
|  |  | • Implement search UI in SharePoint: search bar, real-time suggestions, result cards with title/snippet/metadata, faceted filters & relevance ranking | 3-5 days
|  |  | • Implement per-customer API key & token scoping: each SharePoint tenant gets isolated search API credentials provisioned from CP after auth | 2-3 days
|  |  | • Package SPFx app as .sppkg for SharePoint App Catalog deployment: tenant-wide or site-collection scoped install via App Catalog | 2-3 days
|  |  | • Implement silent background deployment via SPD: after customer authorizes, SPFx package is auto-deployed to their App Catalog without manual steps | 3-4 days
|  |  | • Implement IP protection: SPFx bundle is minified & obfuscated; API routing logic & search business logic not readable from browser source | 2-3 days
|  |  | • Support multi-environment (UAT/PROD): SPFx app reads API URL from CP-provisioned config; switchable without code changes | 1-2 days
|  |  | • Implement error handling & fallback UI: API timeout messages, auth failure prompts, retry logic & admin notification inside SharePoint | 1-2 days
|  |  | • Write deployment & integration guide: step-by-step SharePoint App Catalog install, Azure AD app registration & CP API connection walkthrough | 1-2 days
|  |  | • End-to-end UAT testing: deploy SPFx app on test SharePoint tenant, authenticate via Azure AD, run search queries & validate CP API integration | 2-3 days
MVP - 2 Development | Integrating website content for preprocessing -pipeine in search project - by implementing website as data connector | SPD Portal | • Define website data connector architecture and API contracts for content ingestion | 1-2 days
|  |  | • Implement web crawler and scraper for recursive URL fetching | 2-3 days
|  |  | • Set up authentication (OAuth/API keys) for restricted website access | 1-2 days
|  |  | • Build configuration UI in SPD Portal for website connector settings | 2-3 days
| Modifying the Pre-processing pipeline for web content | SPD Portal | • 1. Data extraction: Implement HTML parsing to extract main text, tables, and media | 2-3 days
|  |  | • 2. Data analysis: Analyze DOM structure to identify headers, footers, and sidebars | 1-2 days
|  |  | • 3. Data cleansing: Remove boilerplate, scripts, styles, and irrelevant HTML tags | 2-3 days
|  |  | • 4. Data preprocessing: Chunk extracted text and normalize encodings for embedding | 2-3 days
|  |  | • 5. Data Enrichment: Generate summaries and extract metadata (title, author, keywords) | 3-4 days
|  |  | • 6. Data Catalog building: Structure processed data into catalog schema for indexing | 2-3 days
|  |  | • Integrate web preprocessing steps into the main GPU-based LLM pipeline | 2-3 days
|  |  | • End-to-end testing of website data connector and preprocessing pipeline | 2-3 days
|  |  | • Deploy web content preprocessing services to GCP instances | 1-2 days
MVP 2 Testing & Refinement | Testing CPD deployment | CPD | • Verify CPD deployment on UAT environment | 1 day
|  |  | • Perform smoke testing for core CPD features | 2 days
|  |  | • Conduct regression testing for existing functionalities | 2 days
|  |  | • Validate production deployment readiness and rollback plan | 1 day
MVP 2 Testing & Refinement | Testing SPD For DIR Web content | SPD | • Test web crawler and content extraction accuracy | 2 days
|  |  | • Validate HTML parsing and boilerplate removal | 1 day
|  |  | • Verify metadata enrichment and summarization for web content | 2 days
MVP 2 Testing & Refinement | Testing the Data collection from customer portal | UCAP & CP | • Validate license and billing data synchronization | 2 days
|  |  | • Test ticketing and activity log data collection | 2 days
|  |  | • Verify admin dashboard data accuracy in UCAP | 1 day
MVP 2 Testing & Refinement | Validating the data at each step in preprocessing pipeline | SPD | • Validate document parsing and chunking accuracy , Metadata Enrichment | 2 days
|  |  | • Test image preprocessing and caption extraction , Metadate Enrichment | 2 days
|  |  | • Verify audio transcription and Metadate Enrichment | 2 days
|  |  | • Validate video frame extraction and Metadate Enrichment | 2 days
|  |  | • Test multimodal LLM Q&A Quality | 3 days
|  |  | • Perform end-to-end pipeline validation with sample datasets | 2 days
Integration & Demo Readiness | Working on E2E validation of from customer creation in UCAP then Customer Onboarding Portal and Customer SPD | UCAP, CP, SPD | • Validate end-to-end customer creation flow from UCAP to Customer Onboarding Portal | 1-2 days
|  |  | • Verify search project deployment and configuration in Customer SPD | 1-2 days
|  |  | • Test data synchronization between UCAP, CP, and SPD during onboarding | 1-2 days
|  |  | • Validate RBAC and permission propagation across all portals | 1-2 days
|  |  | • Perform user acceptance testing for the entire onboarding journey | 2-3 days
|  |  | • Document E2E validation results and sign-off | 1 day
Integration & Demo Readiness | Security & Penetration Testing | All Platforms | • Conduct vulnerability scanning and penetration testing on all deployed services | 2-3 days
|  |  | • Remediate identified security vulnerabilities and misconfigurations | 2-3 days
|  |  | • Perform final security review and sign-off | 1 day
Integration & Demo Readiness | Cost & GPU Usage Monitoring | GCP & Azure | • Set up cost alerts and budgets for GCP GPU instances and Azure App Services | 1 day
|  |  | • Implement GPU utilization tracking and optimization strategies | 1-2 days
|  |  | • Review and optimize resource allocation for production deployment | 1 day
Integration & Demo Readiness | User Documentation & Guides | All Platforms | • Create comprehensive user manuals for Customer Portal and SPD | 2-3 days
|  |  | • Develop API integration guides and developer documentation | 2-3 days
|  |  | • Prepare video tutorials and onboarding materials for end-users | 2-3 days
Integration & Demo Readiness | Disaster Recovery & Rollback | All Platforms | • Define and document disaster recovery procedures and RTO/RPO objectives | 1-2 days
|  |  | • Implement automated database backups and restoration testing | 1-2 days
|  |  | • Formulate and test rollback plans for failed production deployments | 1-2 days
Integration & Demo Readiness | Demo Script & Dataset Prep | All Platforms | • Prepare realistic demo datasets and sample documents for all data connectors | 2-3 days
|  |  | • Develop comprehensive demo scripts highlighting key features and workflows | 1-2 days
|  |  | • Conduct dry runs and refine demo presentation for stakeholders | 1-2 days
DIR-WEB Search Logic
Citation Deep Links routing (Scroll to that section + Highlight of that part )
Prepapre Query Dataset to validate catalog
Validating Catalog through querying to test all the files are reachable
Prepare Autocomplete Question with Catalog + Cananonical Questions
Metadata Enrichment of Child Links in Pages Catalog adaption for this metadata
Unnanu Preprocessing
| Create a structure data based on organization it contains respective organization fields | Github-Oynx prompts | 1. how they create structure data for different organizations
2.how it is use for Unnanu preprocessing stage
3.how much manual task is there
4.which model they use and suggest

## Search-Project-Action-items
Action Items | Status | Assigned To | Reviewer | Due Date | Review By | Modifications | Repo / Platform
[P0} Include contracts data in Search. | Pending | Indra |  | 2026-07-30
Add 2FA as OTP
[P0] Draft Hardware and Software requirements in order to install this product in client | Drafted | Indra |  | 2026-07-30 |  | Prepare Hardware and Software requirements In order to install Search Product in Client.
[P0] Replace MD5 password hashing + stop storing plaintext passwords | Not Started | Indra |  | 2026-07-30 |  | Migrate MD5 to bcrypt/Argon2 with a hash-migration path; remove plaintext password storage in the pass_org column | customer-portal-api; uai-platform-api; uai_platform_onboard_api
[P0] Fix stale CI/CD pipelines post-split | Not Started | Indra |  | 2026-07-30 |  | Add a real deploy stage; remove stale references to the old shared aiu-tenant-runtime-api image name | customer-portal-api; search-project-api
[P1] Connect MySQL/Drupal schema-discovery service to the extractor + wizard | Partial | Indra |  | 2026-07-30 |  | Expose search-project-discovery via the wizard's data-source step; hand off to drupal_mysql.py's extraction path | search-project-discovery; website-processing; search-project-api; search-project-ui
[P1] Fix silent exception swallowing in admin auth middleware | Not Started | Indra |  | 2026-07-30 |  | Replace bare catch in AdminAuthMiddleware.cs:66-70 with logged exception handling so auth failures are visible | uai-platform-api
[P2] Per-customer search-API key provisioning | Not Started | Indra |  | 2026-07-31 |  | Provisioning of search API keys if user provisioned. | search-project-api
[P0] Add real API-key auth + rate limiting to the production search API | Not Started | Indra |  | 2026-07-31 |  | Replace NoOpAuthHandler (Program.cs:52-53) with real API-key validation middleware + a rate limiter | unnanu-web-search-api-v10
[P1] Wire document/image/video/audio pipeline orchestration | Not Started | Indra |  | 2026-07-31 |  | Make SearchProjectProcessingOrchestrator actually call the 5 modality services (Document , Image , Audio, Video , Website) via the existing but unused per-modality ingest_url config table. Provisioning Required LLM models in azure / On-premise. Storing there configuration. | search-project-api
[P1] Build CP -> UCAP sync (licenses/billing/activity/tickets) | Not Started | Indra |  | 2026-07-31 |  | Add entities/API/webhook so customer-portal-api activity flows into UCAP's license/billing/ticket views | uai-platform-api; customer-portal-api
[P0] Provision ML models selected by the user in the search wizard, on‑premise or in Azure. | Not Started | Indra |  | 2026-07-31 |  | In the search project wizard, provision the user‑selected models in the cloud via the infrastructure provisioner. | Search-project-api Infrastructure-provision
[P2] Shared GPU serving stack (vLLM) across modalities | Not Started | Indra |  | 2026-07-31 |  | Share document repo's LLMManager/LOCAL_LLM_URL pattern across image/video/audio/website-processing; provision vLLM on GCP L4/A100 | enterprise-ai-search-document; enterprise-ai-search-image; enterprise-ai-search-video; enterprise-ai-search-audio; website-processing
[P0] Manual Review of Search-Query retrieval evaluation Dataset | Pending | Indra |  | 2026-08-01 |  | Dataset Prepared , need to review
[P0] Rotate plaintext secrets to Key Vault / env vars | Not Started | Indra |  | 2026-08-01 |  | Move DB passwords and API keys out of appsettings.json / appsettings.Development.json into Key Vault refs or env vars | unnanu-web-search-api-v10; uai-platform-api; uai_platform_onboard_api; customer-portal-api; search-project-api
[P1] Video service hardening | Not Started | Indra |  | 2026-08-01 |  | Add Dockerfile, CI pipeline, tests; move default SERVICE_PORT off 8504 (collides with audio) Validatation of Video Processing Service API with local / Open source LLM models. Build Auth layer API , Configuring the service through API. | enterprise-ai-search-video
[P1] Fix image service | Partial | Indra |  | 2026-08-01 |  | Replace stale byte-identical copy of document's pipeline with real mypy/bandit/pip-audit/pytest gates that actually run the 3 existing test files Validatation of Image Processing Service API with local / Open source LLM models. Build Auth layer API , Configuring the service through API. | enterprise-ai-search-image
[P1] Add test suite to document service | Not Started | Indra |  | 2026-08-02 |  | Write a pytest suite matching the README's existing test claim (currently 0 test files) Validatation of Video Processing Service API with local / Open source LLM models. Build Auth layer API , Configuring the service through API. | enterprise-ai-search-document
[P1] website-processing | Partial | Indra |  | 2026-08-02 |  | 29 pytest files exist but nothing runs them on push; only CI file is a cron-only weekly refresh job with no Dockerfile Validatation of Website Processing Service API with local / Open source LLM models. Build Auth layer API , Configuring the service through API. | website-processing
[P1] Resolve EF Core / MySQL provider version constraint | Blocked (external dep) | Indra |  | 2026-08-02 |  | Pomelo.EntityFrameworkCore.MySql has no EF10 release yet; pinned to EF Core 8.x on net10.0 target; decide fallback before EF8 LTS ends Nov 2026 | search-project-api
[P2] Fine-grained RBAC in UCAP | Partial | Indra |  | 2026-08-03 |  | Prepare RBAC Policies for UCAP. Add policy-based [Authorize(Policy=...)] attributes beyond the current binary admin/user check | uai-platform-api
[P2] Fine-grained RBAC in UCSP | Partial | Indra |  | 2026-08-03 |  | Prepare RBAC Policies for UCSP. Add policy-based [Authorize(Policy=...)] attributes beyond the current binary admin/user check | Customer-portal-api
[P2] Consolidated admin dashboard | Not Started | Indra |  | 2026-08-03 |  | Build one unified view combining licenses/tickets/activity/billing/project health instead of separate per-domain pages | uai-platform-ui
[P2] Add frontend test coverage for wizard dev-mode UI | Not Started | Indra |  | 2026-08-03 |  | Only 1 test file / 2 assertions exist, none covering the new dev-mode auth/model/deployment paths | search-project-ui
[P2] Cleanup: delete orphaned mock API files | Not Started | Indra |  | 2026-08-03 |  | Delete unused lib/mock-admin-api.ts and lib/mock-customer-api.ts (not imported anywhere) | uai-platform-ui
[P2] Cleanup: delete leftover scaffold test file | Not Started | Indra |  | 2026-08-03 |  | Delete leftover UnitTest1.cs template test file | search-project-api
[P2] Build S3 connector from scratch | Not Started | Indra |  |  |  | Implement AWSSDK.S3-based connector; currently only a type-literal in lib/types.ts and an explicit stub in CloudAuthService.cs | search-project-api; search-project-ui
[P2] Add deployment slots for zero-downtime deploys | Not Started | Indra |  |  |  | Add slot-swap tasks to azure-pipelines.yml for both API and UI | uai-platform-api; uai-platform-ui
[P2] Close wide-open CORS policy | Not Started | Indra |  |  |  | Replace AllowAnyOrigin/AllowAnyHeader/AllowAnyMethod (Program.cs:63-64) with an explicit allow-list | uai-platform-api
[P2] Implement SharePoint Graph API file sync | Partial | Indra |  |  |  | OAuth token exchange already works; add actual Microsoft Graph API calls to list/sync SharePoint files | customer-portal-api / search-project-api

## Sprint Plan
Sprint | Action item | Platform | Valid sub-task (codebase-grounded) | Priorities | Type | ETA | Codebase anchor / note
Sprint 03 - MVP 2 Development | DIR Web Search accuracy 30% -> 85%+ (file-link metadata + catalog expansion) [IN PROGRESS] | SPD / Search API | Baseline the gold-set eval: run DIR-WEB/eval over gold_queries.csv (85 rows) vs the deployed v2 cascade; confirm start point (v2.0 p@1 29.3) and current v2.2 (p@1 44.8 / p@3 60.3) against the v1 baseline (p@1 56.9 / p@3 70.7) | P1 | VERIFY | 0.5d | DIR-WEB/eval/eval_harness.py (local-only repo); handoff/CONTINUE.md
|  |  | Run queries comparison analysis on When v/s How ? , asking different kind of questions when,where,how,what,why kind of answering quesiton | P1 | VERIFY | 0.2 D
|  |  | Enumerate file links already captured but unused: distinct PDF/DOCX/XLSX URLs from sections.block_links_json + mdta.registration_link + page body | P2 | BUILD | 1d | website-processing schema.sql:120 (block_links_json); enrichment currently EXCLUDES file content
|  |  | Parse the linked files with the existing document pipeline (PyMuPDF/docling OCR + table extraction) — reuse, don't rebuild | P1 | REUSE | 2d | enterprise-ai-search-document/src/processors
|  |  | Enrich extracted file text with the existing 3-model ensemble (summary/abstract/core_topic/intent_keywords); write file-scoped rows | P1 | BUILD | 2d | website-processing/src/enrichment/run_ensemble
|  |  | Add file metadata to schema: link each file to its parent page mdta (nid/source_url) + file title/type/topic columns | P1 | BUILD | 1d | new dir_aiu_web_files / extend dir_aiu_web_mdta (schema.sql:23)
|  |  | Expand catalog: generate/augment cards with file-derived metadata so file-answerable queries route (targets the 11/37 misses not in the v2 corpus) | P1 | BUILD | 2-3d | dir_aiu_web_catalog (schema.sql:216) + catalog generator
|  |  | Re-run the gold eval; target p@1 >85%; bucket residual misses (card gap / floor / ranking) via dir_web_search_trace and iterate | P1 | VERIFY | 1d | dir_web_search_trace; CONFIDENCE_FLOOR=70 / LEX_FLOOR=0.05
| Locate/clone ingestion-pipeline service | SPD | Identify the connector/ingestion backend CP calls (lib/data-source-api.ts uses same base URL as tenant-api); confirm whether it is a separate FastAPI repo in ADO or served by tenant-api | P2 | VERIFY | 0.5d | Customer portal/lib/data-source-api.ts:29
|  |  | Clone it into the workspace (or document it lives inside tenant-api) so connector work has a home | P2 | BUILD | 0.5d | greenfield/locate
| Branch hygiene for preprocessing repos | SPD | Merge document (branch-Y), video (B_video), audio (dev) into their mainline so the dev/uat/main -> env CI mapping fires | P1 | FIX | 0.5-1d | 3 repos on non-standard default branches
| Real authentication on the search API | SPD / Search API | Replace NoOpAuthHandler with an X-Api-Key handler validating against a keys table | P3 | BUILD | 1d | unnanu-web-search-api-v10 Program.cs:53
|  |  | Require the key on dirsearch/v1 and dirsearch/v2; keep /health + swagger anonymous | P3 | CONFIG | 0.5d | SearchController.cs (dirsearch/v1¦v2 routes)
|  |  | Add per-key rate limiting via ASP.NET RateLimiter middleware | P3 | BUILD | 0.5d | greenfield
|  |  | Update db/smoke_test.sh to send the key; assert 401 without it | P3 | VERIFY | 0.25d | unnanu-web-search-api-v10/db/smoke_test.sh
| Per-customer search API key provisioning | CP & SPD | Add a search_api_keys table + key generation on search-project creation in tenant-api | P1 | BUILD | 1d | greenfield (walkthrough contracts only carry GroqApiKey today)
|  |  | Extend SearchProjectWalkthrough contracts to return the provisioned key | P1 | BUILD | 0.5d | SearchProjectWalkthroughContracts.cs
|  |  | Show/copy the key in the CP search-project settings UI | P1 | BUILD | 0.5d | components/search
| Video service hardening | SPD | Write a Dockerfile mirroring audio's (msodbcsql18 + uvicorn FastAPI) | P3 | BUILD | 0.5d | copy enterprise-ai-search-audio/Dockerfile
|  |  | Change default SERVICE_PORT 8504 -> 8505 to end the collision with audio | P3 | FIX | 0.25d | enterprise-ai-search-video config/settings.py
|  |  | Add azure-pipelines.yml (branch->env, ACR push) copying audio's | P3 | BUILD | 0.5d | copy audio azure-pipelines.yml
|  |  | Add a minimal pytest smoke for /process/sync | P3 | BUILD | 0.25d | greenfield (no tests exist)
| Deploy preprocessing on GCP GPU with self-hosted multimodal LLM | SPD | Request GCP GPU quota (L4 to start) day 1; provision instance with CUDA + vLLM | P3 | CONFIG | 1d | blocker if delayed
|  |  | Serve one multimodal model on an OpenAI-compatible endpoint; baseline = the existing self-hosted qwen3-30b | P3 | BUILD | 1.5d | service.unnanu.com:52415 (exo cluster)
|  |  | Point the document service at the GPU endpoint via LOCAL_LLM_URL (already supported) | P2 | REUSE | 0.25d | document src/services/local_llm_service.py:51
|  |  | Replicate the LLMManager local-provider pattern into image, audio, video (they call Gemini/Groq directly today) | P3 | BUILD | 2d | document src/services/llm_manager.py
|  |  | Containerize each modality API (inference is remote, so no GPU in these images) and deploy to Cloud Run/GKE with the endpoint injected via env | P2 | BUILD | 2d | doc/img/audio Dockerfiles exist; video from hardening task
|  |  | Verify each modality /ingest completes against the GPU LLM with no Gemini/Groq call in the path | P2 | VERIFY | 1d
|  |  | IP protection/obfuscation, encrypted config, API gateway | P2 | DEFER | - | not needed for demo -> stretch/post-demo
| Drupal MySQL DB connector (replaces manual XLSX) | SPD | Add a MySQL reader in website-processing (pymysql already used in the image repo) to pull Drupal node/field content | P2 | BUILD | 1.5d | pattern from enterprise-ai-search-image (pymysql>=1.1.1)
|  |  | Map Drupal rows to the existing sections/enrichment input schema | P2 | BUILD | 1d | website-processing/main_pipeline.py
|  |  | Swap ingest_xlsx.py's XLSX source for the MySQL source; keep chunking/enrichment/catalog unchanged | P2 | REUSE | 0.5d | website-processing/ingest_xlsx.py:40 (DEFAULT_XLSX)
|  |  | Parity-check row counts + content vs latest dir-search-catalog-v4.xlsx | P2 | VERIFY | 0.5d
| Website data connector (non-Drupal sites) | SPD Portal | Define the connector interface consistent with existing storage connectors | P3 | BUILD | 1d | align with ingestion service
|  |  | Implement a generic crawler (requests + BeautifulSoup/Playwright) — none exists today | P3 | BUILD | 2-3d | greenfield
|  |  | Add a crawler config step to the SearchProjectWizard connector UI | P3 | BUILD | 1d | components/search/steps
|  |  | Feed crawler output into the existing website-processing enrichment | P3 | REUSE | 0.5d | website-processing
| Web-content pre-processing steps | SPD Portal | Step 1 - HTML extraction: main text, tables, media | P3 | BUILD | 2d | greenfield
|  |  | Step 2 - DOM analysis: identify/strip header, footer, sidebar | P3 | BUILD | 1-2d | greenfield
|  |  | Step 3 - cleansing: remove boilerplate, scripts, styles | P3 | BUILD | 2d | greenfield
|  |  | Steps 4-6 - chunk / enrich / catalog | P3 | REUSE | 0.5d | ALREADY BUILT in website-processing (generate_catalog.py, sections chunker) - DO NOT REBUILD
|  |  | Wire steps 1-3 output into the existing chunker input | P3 | BUILD | 1d
| Data collection CP -> UCAP (moved up from Sprint 5) | UCAP & CP | Add sync-target endpoints in UCAP for license/billing/activity/tickets (controllers already exist) | P1 | BUILD | 2d | uai-platform-api Licenses/Billing/Analytics/Support controllers
|  |  | Build a CP-BE -> UCAP-BE webhook/API on the shared Azure SQL ai-search DB | P1 | BUILD | 2d | same server both point at
|  |  | Reuse AdminAuthMiddleware + aiu_unnanu_tokens for RBAC so Unnanu admin sees all CP data | P1 | REUSE | 0.5d | AdminAuthMiddleware
|  |  | Expose consolidated data endpoints the UCAP admin dashboard will read | P1 | BUILD | 1d
| Un-mock UCAP UI | UCAP FE | Replace mock-admin-api.ts / mock-customer-api.ts calls with real fetches via lib/api-service.ts | P1 | FIX | 1.5d | uai-platform-ui/lib/mock-admin-api.ts, mock-customer-api.ts, api-service.ts
|  |  | Wire real auth (auth-context) to uai-platform-api signin | P1 | BUILD | 0.5d | NEXT_PUBLIC_ADMIN_API_BASE_URL
|  |  | Delete the mock modules once dashboards read live data | P1 | FIX | 0.25d
| Drupal web-search package (unnanu_search) | SPD | Confirm the secured REST API exposes query/suggest/health (depends on the auth task) | P1 | VERIFY | 0.25d | SearchController dirsearch/v2
|  |  | Scaffold a Composer-installable Drupal 10 module | P1 | BUILD | 1.5d | greenfield
|  |  | Admin config form: API URL, API key, project ID, environment | P1 | BUILD | 1d | greenfield
|  |  | Search block + results page calling dirsearch/v2 with filters/pagination | P1 | BUILD | 1.5d | greenfield
|  |  | API-key auth + auto-injection of the API URL from the SPD project config | P1 | BUILD | 1d | depends on key provisioning
|  |  | Composer packaging + versioned release; install docs; UAT on a throwaway Drupal site | P1 | BUILD | 1.5d
|  |  | Module IP obfuscation | P1 | DEFER | - | stretch
■ SPRINT 04 - MVP 2 TESTING & REFINEMENT ■
| Clone DIR-WEB eval harness | SPD | Clone DIR-WEB (only existing Q&A quality harness, web-only) into the workspace |  | REUSE | 0.5d | referenced in unnanu-web-search-api-v10/handoff, not cloned
| Bootstrap pytest in the document repo | SPD | Add a minimal pytest suite (README claims pytest; zero test files exist) |  | BUILD | 1d | enterprise-ai-search-document
| Validate each preprocessing step | SPD | Build per-modality fixtures (doc/img/aud/vid) |  | BUILD | 1d
|  |  | doc: assert chunk counts + metadata columns in dir_aiu_doc_sections |  | VERIFY | 0.5d
|  |  | img: extend the existing pytest suite with caption assertions |  | REUSE | 0.5d | image repo has real tests
|  |  | aud/vid: assert transcript / frame + sections rows (video needs fixtures first) |  | VERIFY | 1d
|  |  | Multimodal Q&A quality via the DIR-WEB harness |  | VERIFY | 1d | depends on DIR-WEB clone
|  |  | End-to-end pipeline run on sample datasets (doubles as demo-data prep) |  | VERIFY | 1d
| Test SPD DIR web content | SPD | Parity: MySQL/crawler output vs the XLSX baseline |  | VERIFY | 1d
|  |  | Boilerplate-removal correctness on sample pages |  | VERIFY | 0.5d
|  |  | Enrichment/metadata present (reuse existing website-processing pytest) |  | REUSE | 0.5d
| Test CPD (onboarding) deployment | CPD | Run the onboarding wizard E2E on UAT; verify Terraform provisions tenant infra |  | VERIFY | 1d | OnboardingController/ProvisioningController + Terraform GCP
|  |  | Smoke + regression on the onboarding + provisioning endpoints; validate rollback |  | VERIFY | 1d
| Test CP -> UCAP data collection | UCAP & CP | Seed license/ticket/billing/activity in CP -> assert they surface via the UCAP API |  | VERIFY | 1.5d | now testable (build moved to Sprint 3)
|  |  | Verify UCAP dashboard accuracy after the un-mock |  | VERIFY | 0.5d | depends on un-mock task
■ SPRINT 05 - INTEGRATION & DEMO READINESS ■
| Separate CP and SPD into 4 repos | Customer Portal | Follow the onboard-repo extraction pattern (documented, proven) |  | REUSE | 0.5d | uai_platform_onboard_* READMEs
|  |  | Extract SPD FE = app/dashboard/search + components/search¦unnanu_ui_package¦customer_ui_package into a new repo |  | BUILD | 1d
|  |  | Extract SPD BE = SearchprojectwalkthroughController + SearchProjectWalkthroughService (~4400 LOC) + 3 orchestrators + CatalogGenerationService |  | BUILD | 1d
|  |  | CP FE = remaining app/dashboard; CP BE = TenantAccounts/CustomerData/TenantSetup controllers |  | BUILD | 1d
|  |  | Upgrade tenant-api + onboard-api .NET 8 -> 10 on a branch, gated by the walkthrough E2E test |  | BUILD | 1d | currently .NET 8
|  |  | Retain shared shadcn/ui components + lib/api.ts base-URL resolution (never change) |  | REUSE | 0.5d | lib/api.ts
|  |  | 4 azure-pipelines.yml (branch->env ACR) + independent build/test green |  | BUILD | 1d
| DevOps: Azure UAT & PROD for all 8 repos | All platforms | Create 16 App Services (8 repos x UAT/PROD) |  | CONFIG | 1d
|  |  | Migrate tenant-api off GCP Cloud Run onto Azure App Service (its azure-pipelines.yml is legacy) |  | FIX | 1d | aiu-cust-api-tr32 -> Azure
|  |  | CORS, HTTPS/TLS1.2+, deployment slots, App Insights + health checks for all 8 |  | CONFIG | 1.5d | App Insights absent everywhere today
| Rotate plaintext credentials | All BE | Rotate DB creds committed in appsettings.json (uai-platform-api, onboard-api, both search APIs) and move to Key Vault references |  | FIX | 1d | handoff/SECURITY-secrets-migration.md
| Replace MD5 password hashing | CP BE | Swap MD5 for bcrypt/Argon2 + migrate existing hashes on next signin |  | FIX | 0.5-1d | TenantSetupController.cs:89
| Fix the image repo's stale pipeline | SPD | Wire the real mypy/bandit/pytest gates its README claims (currently a byte-copy of document's) |  | FIX | 0.5d | enterprise-ai-search-image/azure-pipelines.yml
| Demo storage connectors (GCS, S3, SharePoint) | SPD | GCS: implement using Google.Cloud.Storage.V1 (already in tenant-api csproj) |  | BUILD | 1.5d | tenant-api csproj has the SDK
|  |  | S3: add AWSSDK.S3 (only RDS/ECS present today) + bucket list/read/index |  | BUILD | 1.5d | s3' type exists in lib/types.ts
|  |  | SharePoint: reuse the existing OAuth callback + MS Graph read |  | BUILD | 2d | app/oauth/callback + 'sharepoint' type in lib/types.ts
|  |  | Wire all into the settings/connectors + sources UI (types already defined) |  | REUSE | 1d | lib/types.ts
|  |  | Connector health monitoring + E2E ingest->search per connector |  | VERIFY | 1.5d
| SharePoint SPFx search app | SPD | Build the SPFx React web part (greenfield; no SPFx code exists) |  | BUILD | 4d | greenfield
|  |  | Azure AD OAuth2 — reuse the existing SharePoint OAuth app registration |  | REUSE | 2d | app/oauth/callback
|  |  | Integrate with the search API using the per-customer key (depends on Sprint 3 auth + key provisioning) |  | BUILD | 2d
|  |  | Package as .sppkg + silent auto-deploy via SPD + UAT on a test SharePoint tenant |  | BUILD | 3d | procure M365 dev tenant early
| E2E validation UCAP -> CPD -> SPD | UCAP, CP, SPD | Drive the full flow: customer creation in UCAP -> onboarding -> SPD project deploy -> connector ingest -> search |  | VERIFY | 1.5d | flow exists end-to-end today
|  |  | Validate RBAC/permission propagation + document sign-off |  | VERIFY | 0.5d
| Security & penetration testing | All platforms | Fix the 4 known issues BEFORE the scan: creds, NoOpAuth, MD5, localStorage session |  | FIX | 0.5d | cross-ref rotate/MD5/auth tasks
|  |  | Run vulnerability scan + pentest, remediate, final sign-off |  | VERIFY | 2d
| Cost & GPU monitoring | GCP & Azure | GCP budgets + Cloud Monitoring for GPU utilization/latency; Azure cost alerts |  | CONFIG | 1-2d
| User documentation & guides | All platforms | CP + SPD user manuals and API integration guides (only dev READMEs exist today) |  | BUILD | 2-3d | greenfield
|  |  | Video tutorials |  | DEFER | - | cut from demo scope
| Disaster recovery & rollback | All platforms | Test Azure SQL backup restore (built-in backups exist; restore never tested) |  | VERIFY | 1d
|  |  | PROD rollback runbook (keep as P0; full DR drills deferred) |  | BUILD | 1d
| Demo script & dataset prep | All platforms | Build demo datasets per modality/connector (none exist in any repo) |  | BUILD | 2d | greenfield
|  |  | Write the demo script + 2 dry runs |  | BUILD | 1-2d
■ BACKLOG - SPRINT 07/08 ■
| Deferred storage connectors | SPD | OneDrive, Google Drive, Snowflake, BigQuery, Redshift, Synapse, Dropbox, Box, SFTP/NFS |  | DEFER | - | cut from Sprint 5 demo scope; some UI types already exist in lib/types.ts
| Define action items for Sprints 6, 7, 9, 10 | All platforms | Scope Stakeholder Demo, Feedback, Pilot Deployment, Production Readiness (sheet currently empty) |  | BUILD | - | scope Sprints 9-10 before Sprint 8 ends

## Jama_action_items
Date | Action Items | Status | ETA

## Indra Action items
Priority | Details | Review | Status | Due Date | Assinged | Comments | Onedrive or other Links | Comments
| Evaluation and Manual Review of 300 Golden Dataset | Indra
| Evaluation of LLM Models for Profile Creation | Indra |  |  | Jama
Architecture Diagrams for Product Wise

## Services Naming Standards
Product | Envrironmnet | Component / Function | Azure Services | Service Name | Remarks

## Professional_Friend_Project
Action Items | Sub Tasks | Status | Note | Tools / Languages / Frameworks
1. 3D Avatar & Virtual Environment Rendering | • Load Ready Player Me avatar (aura.glb) with 52 Apple ARKit blendshapes • Retarget and loop Mixamo FBX animations (Greeting, Talking, Happy, Clapping, Dancing, Sitting Interview) • Build interactive 3D Office (Cyber Chair, Desk, Laptop, Bookshelf) and Nature environments • Configure PBR lighting, PMREM RoomEnvironment, and Three.js OrbitControls | Completed | Stripped mixamorig bone prefixes for seamless retargeting. Fixed avatar orientation to face forward (rotation.y = 0). | Three.js, WebGL 2.0, GLTFLoader, FBXLoader, React 19, TypeScript
2. Real-Time Biometric Face Tracking & Emotion Detection | • Client-side Google MediaPipe FaceLandmarker running at 60 FPS • Extract 478 3D facial landmarks and live gaze vector • Classify candidate emotional states (Neutral, Happy, Surprised, Sad, Focused) • Synchronize candidate visual feedback with interviewer prompt context | Completed | Runs entirely client-side via WASM with zero server latency and 100% user privacy. | @mediapipe/tasks-vision, WebRTC MediaDevices, HTML5 Canvas, TypeScript
3. Real-Time Environment Object Detection | • Real-time webcam object detection via TensorFlow.js COCO-SSD • Identify physical objects (laptop, cell phone, book, cup, chair, person) • Inject detected objects into LLM prompt for environmental grounding | Completed | WebGL hardware acceleration with dynamic confidence threshold filtering and bounding boxes. | @tensorflow/tfjs, @tensorflow-models/coco-ssd, WebGL backend
4. Real-Time Technical Interview & Dynamic Question Generation | • Dynamic 15-question interview bank generation for top tech companies (Meta, Google, Apple, OpenAI) • Live Google Search Grounding with Gemini 2.5 Flash for verified real-time citations • Fallback question compilation via Mistral Large • Contextual candidate assessment based on emotion, role, and turn history | Completed | Questions categorized into Coding, System Design, Behavioral (STAR), and Domain-specific technical questions. | @google/genai (Gemini 2.5 Flash), Google Search Grounding, Mistral Large API, TypeScript
5. Multi-Band Conversational Lip-Sync & Formant Calibration | • Real-time Web Audio FFT frequency formant analyser (200Hz-8000Hz) • Dynamic ARKit blendshape modulation (jawOpen, mouthFunnel, mouthSmile, mouthPucker) • Calibrate jawOpen bound to 0.05-0.35 to prevent unhinged/wide mouth opening • Parallel NVIDIA Audio2Face blendshape streaming integration | Completed | Natural human conversational bounds applied across all vowel and consonant formants. | Web Audio API (AudioContext, AnalyserNode), Apple ARKit 52 Blendshapes, NVIDIA Audio2Face
6. Speech Interruption & Overlapping Speech Cancellation | • Implement stopSpeaking() to immediately halt active Web Audio nodes • Reset speech queue (speakQueueRef) and discard pending in-flight audio • Advance speech turn ID (currentSpeechTurnRef) to invalidate stale responses • Auto-interrupt speech on mic click when candidate starts speaking | Completed | Completely eliminates double-voice overlap and response collision when new messages arrive. | Web Audio API, React Refs, JavaScript Promises, TypeScript
7. Standalone Port 3000 Architecture & Direct Vite Cloud Proxies | • Eliminate port 3001 Express server dependency for 100% standalone frontend execution • Configure direct Vite cloud proxies (/api/mistral, /api/deepgram, /api/groq, /api/cartesia) • Setup single-entry environment variables (envPrefix in vite.config.ts) • Remove unused packages (better-sqlite3, fbx2gltf, express, http-proxy-middleware) | Completed | Simplified development workflow: single command execution (npm run dev) on port 3000. | Vite 6, Tailwind CSS v4, TypeScript, React 19